## Slide 1: Childhood Development Initiative
DCYA Update
June 24th 2015

## Slide 2: Overview
* Phase One activities and outcomes (2007-2012);
* Bridging phase (2013-2014)
* ABC activities, successes and challenges (2014-2016).

## Slide 3: Phase One
  Seven services designed, delivered and evaluated;
  Eight evaluation reports and eleven policy papers published;
  Round table discussions held with senior policy influencers for each evaluation
  Advisory committee established for 3 services

## Slide 5: Bridging Phase
Maintaining services while evaluation reports finalised and conclusions interpreted;
Mate-tricks de-commissioned;
Healthy Schools and CSI reduced and ceased;
Continuation of advisory committees.

## Slide 7: ABC Phase: Key Principles
Continuation and replication of proven or promising models;
No further local evaluation - monitoring to be undertaken centrally by Pobal and CES;
Focus on sustainability of programmes, and their integration into existing structures and mainstream services;
Collaboration with other sites;
Mainstreaming to be undertaken centrally.

## Slide 8: Identification of Core Activities:
Primarily based on recommendations from independent evaluations;
Negotiations with DCYA and AP;
Requirement to reduce submission costs by 20% (May 2013);
Reduction in CDI staffing.

## Slide 9: Core Activities 2013-2016:
Parent support in early years;
Early intervention speech and language service;
Doodle Den;
Doodle Families;
Restorative Practice Strategic Development;
Ante Natal to Three Initiative (ATTI);
Families Imprisonment Parenting Programme (KHF funded);
Sharing the learning.

## Slide 10: Parent Support in Early Years
Nine PCFs supported in nine EY services;
Brief widened to engage other families from neighbouring EY services/schools/health centres;
Focus on formal and informal parenting courses and accessing external agencies;
Quality assurance and support primarily though South Dublin CCC.

## Slide 11: PCF Challenges
Sustainability of service in TW;
Integration of the model into other structures and services.

## Slide 12: Early Intervention Speech and Language
Two SLTs employed;
South Dublin CCC employment ceased;
Working in 10 EY services (including an Early Start) and three Primary schools;
Caseload of approx. 140 children;
Deliver parent and staff training, formal and informal;
Support SDCCC in delivering annual/bi-annual training to parents/staff in wider area.
Participating in follow-up evaluation.

## Slide 13: SLT Challenges
Employment of SLTs through CCC;
Comparative evaluation of CDI and HSE SLT services highly problematic;
Offer to fund additional SLT post within HSE not progressed.

## Slide 14: Doodle Den
After school literacy programme for 5-6 year olds;
Currently 20 groups running in 4 counties;
Some groups identified alternative sources of funding.

## Slide 15: Doodle Den: Challenges
Review of SCP ongoing, lack of clarity re its ongoing role;
Reduced funding of SCP;
Specific funding issues in three Ballyfermot schools;
Identification of appropriate structures for delivery;
Capacity building to quality assure delivery.

## Slide 16: Doodle Den Plus
Identified locally in order to sustain benefits for children;
Consultation process involved:
  Local agencies and parents
  Policy/’expert’ groups
  Literature review
Pilot completed and Mary Immaculate evaluating implementation;
For roll out autumn 2015.

## Slide 17: Restorative Practice Strategic Development
  Two strands of work:
    Capacity building in TW;
    All-Ireland strategic forum to promote RP, progress quality assurance and accreditation.

## Slide 18: Restorative Practice Strategic Development
  www.restorativepracticesireland.ie
  Publication of quality standards
  Commissioned development of FETAC modules
  Oberstown working to become a restorative community

## Slide 19: RP Challenges
  Irish Accreditation
  Embedding the approach across disciplines
  Mechanisms to quality assure practice

## Slide 20: ATTI
Prompted by a recognition that this is a central phase of development;
Consultation process involved:
  Local agencies and parents;
  Policy/’expert’ groups;
  Literature review.
Logic model agreed, steering committee established and links established with KHF development.

## Slide 21: Sharing the Learning
Continued delivery of generic and tailored workshops based on CDI’s ‘Quality Services. Better Outcomes’ workbook;
Plans to develop a further module on an integrated evaluation framework.

## Slide 22: Next steps?
Opportunities to support replication of proven programmes;
Role in mentoring new ABC areas and other communities?
Local consultation on next phase;
Review of SLT needs in TW;
Mainstreaming discussions (local and national);
Strategic research proposal submitted.